## RAIL
Updated: | 2018-10-17
Task Number | MS or Risk Number | Specific Task (and Deliverable) | Assigned | Due | Closed | Status (W/C/H/PD) | Owner/ Responsible | Detailed Description of Work | Needed Resources | Action Log (with hours)
T0 | M0 | Specific task, including the deliverable | MM/DD/YY | MM/DD/YY | MM/DD/YY | Current status of the task: Working, Closed, On Hold, Past Due | One individual | For example: I will read and summarize the following three papers on battery/super capacitor hybrids; I will create a one page report for each paper: ... | For example: supplies and purchased items, dependencies on completions of other tasks, additional training and knowledge | MM/DD/YY: Bob did this (3 hr) MM/DD/YY: Bob contacted the vendor (1 hr) MM/DD/YY: Bob completed the task
T1 | M1 | Kickoff Meeting: Presentation with interviews and questions | 2018-09-02 | 2018-09-23 |  | Complete | Joel Goodin | Joel will create interview questions and review them with the team. | Knowledge from first responders | 09/10/18: Redkar receved due dates from client 09/12/18 Team received expected due dates from Redkar 09/12/18 Redkar sent team contact information to client
T2 | M36 | Define Goals and Expectations: Goals of the group and timeline are created | 2018-09-02 | 2018-09-24 |  | Complete | Miguel Ortega | Miguel will make sure that the goals and expectations of the teams are agreed upon and solidified. We made the schedule, and we agreed on on the days we will meet and complete team assignments. These can be found in my E-notebook, and in the GANT chart | Meet with our teams and get thier input to make sure that this is done | 9/17/18: Team meeting is held and some of the responibilities and tasks are assigned 9/19/18: Our goals are defined and we make our schedule and stretch goals in the team meeting
T3 | M12 | Problem Definition: Assignment is completed and turned in | 2018-09-01 | 2018-09-24 |  | Complete | Jacob Knaup | Jacob will make a problem definition which the team will calloborate on to make sure that it meets the needs of the user and we address the problem | Meeting times will be needed in order to make sure that we all collaborate on the pproblem definition | 9/05/18: Jacob has made a draft of the problem definition 9/12/18: The team meets and we look over the status report and make some adjustements. We will return to it after the kickoff meeting to make sure that it addresses the need 9/21/18: Jacob created a presentation with the required slides and layout for the problem definition and scope assignement 9/23/18: Jacob and Michaeala filled in the problem definition and scope presentation 9/23/18: Jacob submitted the presentation
T4 | M37 | Brainstrom & Decide on Concepts: Technologies are researched, The Air Force has answered all questions, and possible demos are seen | 2018-09-24 | 2018-10-01 |  | Hold | Michaela |  | Knowledge of various solutions that exist and what first reponders need. Details of expectations for the competition.
T5 | M38 | Obtain Hardware: Get the sensors we need. | 2018-10-24 | 2018-11-10 |  | Complete | Miguel Ortega | We have requested Professor Redkar to go ahead abd purchase the main sensor used for our product ahead of the purchasing of all other equipment | Ask Redkar to purchase our product early since it is one of the few of its kind and reseearch how to use the type of sensor we have asked for. | 9/26/18: We were able to get a microwave sensors and we are testing them. We are also done researching some sensors 10/1/2018: We are calling and messaging companies who dabble in this tech in order to gain more of an insight as to how they use the sensors/radars to make their products work. We are able to find only limited numbers of technologies that can do this for us, and we want to make sure we are using the best tech that we have. 10/10/18: We all came together after the interview and discussed all the possible solutions that were available. 10/17/2018: We have yet to choose a tech, but we are putting all of our efforts towards choosing the correct tech. We do not want to invest in the wrong tech and lose money. 10/24/2018: We have decided which hardware we want to use. 10/31/2018: Ancortek radar has come in and we are able to play with hardware
T6 | M40 | Concept Drawing: Diagram of the device we plan to make, highlighting the technologies we plan to incorporate | 2018-09-12 | 2018-10-08 |  | Complete | Miguel Ortega | We were able to sign up for a radar tech through Redkar and we are hoping to highlight the major components of the radar and see where we can improve. | A plan for what we are making and what specific technologies we will incorporate into it | 9/24/2018: We signed up for a class that is all about radar tech. We are hoping to highlight the major parts of the tech and improve on where we need to. 10/1/2018: We are all contacting companies to ask about specific details regarding possible development boards and sensors 10/5/2018: We had to complete the device and specifications sheet which meant that we had to have technologies and specifications of the device confirmed. We were able to get that all set and done, and all the information is on the powerpoint provided.
T7 | M37 | Order samples: We have placed orders or arranged to receive samples of the critical hardware we want to investigate | 2018-09-12 | 2018-10-12 |  | Complete | Jacob Knaup | We need to decide which components, especially sensor technologies, we feek are promising and order them to try out and test. This will require us to research different products, report our results, and make a selection as a team. | We need access to our budget and we need information regarding which parts we want | 9/26/18: Dr. Redkar orered and received some parts for us that he chose 9/27/18: Miguel & Michaela began testing the sensors we were provided. She constructed a simple circuit to power the sensor using a PSOC pioneer kit. She and Jacob tested the sensors with an LED and found that the range was drastically less than advertised. Jacob and Michaela consulted with Dr. Pollat and he suggested that we increase the supply voltage and run the output into a high impedance load. 9/28/18: Jacob and Michaela connected the sensors to benchtop tools and were able to successfully test them. They worked correctly, however their intended use is not our application and they will not be sufficiant 10/1/18: We met and decided to pursue the MIT coffee can radar. Jacob and Miguel researched the parts it requires and its performance 10/3/18: We met and decided to reach out to contacts for 4 different technologies we will pursue - the coffee can radar, Xethru, Walobot, and DEVRAD. We will select which of these products to order based on the contacts' responses 10/10/18: After contacting the contacts we met up and reported our findings. The DEVRAD is not suitable for through-wall use and is out of consideration. We were also advised against the coffee can radar, so that is out, leaving only the Xethru and Walabot 10/12/18: We were not able to meet with Redkar this week, ut next week we are meeting on Monday and will decide on which product to order 10/15/18: Dr. Redkar decided he wanted to do more research before we make a decision 10/17/18: Dr. Redkar found another product that he would like to investigate and consider buying. Therefore, our decision is being delayed further 10/24/18: We ordered the Ancortek radar. On Monday we will decide if we are ordering any parts to build a custom radar.
T8 | M41 | Prepare Design Briefing and Paper: Write out and place in slide show our progress thus far on the project | 2018-09-12 | 2018-10-12 |  | Hold | Joel Goodin
T9 | M42 | Prepare PDR presentation: Make slide show for preliminary design review | 2018-09-12 | 2018-10-15 |  | Past Due | Jacob Knaup | We need to prepare a slide show for our preliminary design review with the Air Force. We don't know what exactly is expected for this slide show other than concept drawings. However, we intend to showcase the tehnologies and components we plan to use. | We need knowledge of what technologies/components we are using and what our device will look like. | 10/12/18: We have not started on this yet, unfortunately, because we are waiting until we meet and discuss our product selection 10/15/18: We have not decided on our product yet and so we have not began this yet 10/24/18: We have not yet scheduled the PDR but it will be next month. I am studying radar terminology so that we can explain our choice. Michaela is preparing a concept drawing. 11/9/18: We have placed all of our concept selectio and benchmarking research into the presentation. We just need to add the demo work that we have done with the radar now that we have received it.
T10 | M44 | Begin official BOM: Proper research on the technology and other aspects of the project completed, some tests and demos prove that what we order will work | 2018-09-12 | 2018-11-02 |  | Hold | Michaela
T11 | M45 | Start Ordering Final Parts: | 2018-09-12 | 2018-11-05 |  | Hold | Joel Goodin
T12 | M2 | Preliminary Design Review | 2018-10-21 | 2018-11-18 |  | Hold | Jacob Knaup |  |  | 10/24/18: We have not scheduled this yet but it will be within the first three weeks of November 11/9/18: The preliminary design review is scheduled for next Wednesday
T13 | M46 | Subsystem Proof of Concept | 2018-09-12 | 2018-11-19 |  | working | Miguel Ortega | We must order the developer boards and all the items by 10/10/2018 in order to start our proof of concept. We are currently calling multiple companies to find the best possible solutions. This is so we do not order a weak or defective device that is not capable of doing what we want it to do. | More information on developer boards out there. More inofrmation on what we can use. How exactly the boards work, and data that the boards or sensors provide and how we will conver it. | 10/10/2018: We meet and discussed each of our discoveries regarding each board. I believe we are going with the board Jacob got because of the strong ability to read through object. We will finalize the decision on Monday. 10/17/2018: We have yet to decide on a technology to create our proof of concept, but we are getting closer and closer. There is an expensive piece of hardware we want to buy, but we are asking many questions, and doing so much research to make sure that we choose the right one. We absolutely do not want to choose a piece of hardware that does not work, so we have dedicated more time to making this work. We will email the comany with many of our questions and hope the response answers all of our questions 10/24/2018: Today we have decided to choose the product we will use in our design. Since it is a product that only needs to be programmed, we will make a small prototype of the actual radar to demonstrate understanding of how the product we are using works. This is because we will not have the time to build something similar to what the product can already do. Thus, we will have a proof of concept developed hopefully by mid November 10/31/2018: We are able to get a reading from the Ancortek device through their SDK. Device is even able to map velocity and distance through a thick wall 11/5/2018: We were able to do some light research and discover a few of the hidden features of the device. We are excited to present how far we have gotten to the IP's
T14 | M47 | Subsystem Demonstration | 2019-01-01 | 2019-01-14 |  | Hold | Michaela
T15 | M48 | Subsystem Integration | 2019-01-01 | 2018-01-28 |  | Hold | Joel Goodin
T16 | M49 | Prepare Critical Design Review | 2019-01-01 | 2018-01-30 |  | Hold | Jacob Knaup
T17 | M50 | Integrated Testing | 2019-01-01 | 2018-02-27 |  | Hold | Miguel Ortega
T18 | M3 | Critical Design Review | 2018-01-13 | 2019-02-10 |  | Hold | Miguel Ortega
T19 | M4 | Hazard Analysis | 2018-09-12 | 2019-03-03 |  | Hold | Jacob Knaup
T20 | M5 | Final Report | 2018-09-12 | 2018-03-24 |  | Hold | Team
T21 | M6 | Final Presentation: | 2018-09-12 | 2019-03-24 |  | Hold | Team
T22 | M7 | Competition: Eevry Milestone is complete | 2019-04-07 | 2019-04-14 |  | Hold | Team
T80
T81
T82
T83
T84
T85
T86
T87
T88
T89
T90
T91
T92
T93
T94
T95
T96
T97
T98
T99
T100
T101
T102
T103
T104
T105
T106
T107
T108
T109
T110
T111
T112
T113
T114
T115
T116
T117
T118
T119
T120
T121
T122
T123
T124
T125
T126
T127
T128
T129
T130
T131
T132
T133
T134
T135
T136
T137
T138
T139
T140
T141
T142
T143
T144
T145
T146
T147
T148
T149
T150
T151
T152
T153
T154
T155
T156
T157
T158
T159
T160
T161
T162
T163
T164
T165
T166
T167
T168
T169
T170
T171
T172
T173
T174
T175
T176
T177
T178
T179
T180
T181
T182
T183
T184
T185
T186
T187
T188
T189
T190
T191
T192
T193
T194
T195
T196
T197
T198
T199
T200
T201
T202
T203
T204
T205
T206
T207
T208
T209
T210
T211
T212
T213
T214
T215
T216
T217
T218
T219
T220
T221
T222
T223
T224
T225
T226
T227
T228
T229
T230
T231
T232
T233
T234
T235
T236
T237
T238
T239
T240
T241
T242
T243
T244
T245
T246
T247
T248
T249
T250
T251
T252
T253
T254
T255
T256
T257
T258
T259
T260
T261
T262
T263
T264
T265
T266
T267
T268
T269
T270
T271
T272
T273
T274
T275
T276
T277
T278
T279
T280
T281
T282
T283
T284
T285
T286
T287
T288
T289
T290
T291
T292
T293
T294
T295
T296
T297
T298
T299
T300
T301
T302
T303
T304
T305
T306
T307
T308
T309
T310
T311
T312
T313
T314
T315
T316
T317
T318
T319
T320
T321
T322
T323
T324
T325
T326
T327
T328
T329
T330
T331
T332
T333
T334
T335
T336
T337
T338
T339
T340
T341
T342
T343
T344
T345
T346
T347
T348
T349
T350
T351
T352
T353
T354
T355
T356
T357
T358
T359
T360
T361
T362
T363
T364
T365
T366
T367
T368
T369
T370
T371
T372
T373
T374
T375
T376
T377
T378
T379
T380
T381
T382
T383
T384
T385
T386
T387
T388
T389
T390
T391
T392
T393
T394
T395
T396
T397
T398
T399
T400

## Gantt Chart
Updated: | 2018-10-17
Milestone or Deliverable |  | Resp Initials | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22
Number | Title |  | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due
Airforce Tasks and Deliverables
M1 | Kickoff Meeting |  | 2018-09-17: 2018-09-23
M2 | Preliminary Design Review |  | 2018-11-12: 2018-11-18
M3 | Critical Design Review |  | 2019-02-04: 2019-02-10
M4 | Hazard Analysis |  | 2019-02-25: 2019-03-03
M5 | Final Report |  | 2019-03-18: 2019-03-24
M6 | Final Presentation |  | 2019-03-18: 2019-03-24
M7 | Competition |  | 2019-04-08: 2019-04-14
Class Deliverables
M11 | PM Tools |  | 2018-09-17: 2018-09-21
M12 | Problem Definition |  | 2018-09-24: 2018-09-24
M13 | Individual Status Report |  | 2018-09-24: 2018-09-28
M14 | enotebook check |  | 2018-10-01: 2018-10-01
M15 | Fall Break Team Status Report |  | 2018-10-01: 2018-10-05
M16 | Requirements and Specifications |  | 2018-10-08: 2018-10-08
M17 | Individual Status Report 2 |  | 2018-10-08: 2018-10-12
M18 | Problem Definition Paper |  | 2018-10-15: 2018-10-15
M19 | Design Briefing Presentation |  | 2018-10-15: 2018-10-15
M20 | Team Status Report |  | 2018-10-15: 2018-10-19
M21 | Reflection of Design Briefing |  | 2018-10-22: 2018-10-22
M22 | Individual Status Report 3 |  | 2018-10-22: 2018-10-26
M23 | Design Review Slides |  | 2018-10-29: 2018-10-29
M24 | Concept Selection Paper |  | 2018-10-29: 2018-10-29
M25 | CATME |  | 2018-10-29: 2018-10-29
M26 | Team Status Report |  | 2018-10-29: 2018-11-02
M27 | Individual Status Report 4 |  | 2018-11-05: 2018-11-09
M28 | enotebook check |  | 2018-11-12: 2018-11-12
M29 | Team Status Report |  | 2018-11-12: 2018-11-16
M30 | Final Report |  | 2018-11-26: 2018-11-26
M31 | Final Presentation Slides |  | 2018-11-26: 2018-11-26
M32 | Individual Status Report |  | 2018-11-26: 2018-11-26
M33 | CATME |  | 2018-12-03: 2018-12-03
Project Milestones and Deliberables
M36 | Define Goals and Expectations for Device |  | 2018-09-24: 2018-09-24
M37 | Brainstorm and Decide on Concepts |  | 2018-10-01: 2018-10-01
M38 | Choose Sample Hardware |  | 2018-10-01: 2018-10-05
M39 | Order Samples |  | 2018-10-08: 2018-10-12
M40 | Concept Drawing |  | 2018-10-08: 2018-10-08
M41 | Prepare Design Briefing and Paper |  | 2018-10-08: 2018-10-12
M42 | Prepare PDR Presentation |  | 2018-10-15: 2018-10-15
M43 | Air Force Preliminary Design Review |  | 2018-10-22: 2018-10-22
M44 | Begin Official BOM |  | 2018-10-29: 2018-11-02
M45 | Start Ordering Final Parts |  | 2018-11-05: 2018-11-05
M46 | Subsystem Proofs of Concept |  | 2018-11-19: 2018-11-19
M47 | Subsystem Demonstration |  | 2019-01-14: 2019-01-14
M48 | Subsystem Integration |  | 2019-01-28: 2019-01-28
M49 | Prepare Critical Design Review |  | 2019-01-28: 2019-01-30
M50 | Integrated Testing |  | 2019-02-25: 2019-02-27
M51
M52
M53
M54
M55
M56
M57
M58
M59
M60
M61
M62
M63
M64
M65
M66
M67
M68
M69
M70
M71
M72
M73
M74
M75
M76
M77
M78
M79
M80
M81
M82
M83
M84
M85
M86
M87
M88
M89
M90
M91
M92
M93
M94
M95
M96
M97

## Risk Log
Updated: | 2018-09-17
Risk Number | Triggered (Y/N) | Description of Risk | Owner/ Responsible | Type | Severity (H/M/L) | Response (Avoid, Mitigate, Accept) | Status
R0 | N | Specific issue that puts the project outcome at risk | One Individual | Financial, Schedule, Technical, Expertise, Other | High, Med, Low | Avoid, Mitigate, Accept | Monitoring, or actions (with task numbers) taken to mitigate the risk
R1 | N | A Misunderstanding between the Airforce and our Team | Joel | Schedule | Low | Avoid | Make sure we are in constant contact with our IP in order to mitigate the risk of this happening. We will also ask as many questions as we can
R2 | N | Technical expertise with new sensors tech is low | Miguel | Expertise | High | Mitigate | Make sure we do research on the tech and get hands on time to assure we know what we are doing with the tech. We have researched some of the sensors, and we are currently messing around with microwave sensor tech.
R3 | N | Going overbudget on ordering any tech | Michaela | Financial | Low | Accept | Make sure that we keep a spreadsheet full of expense up to date
R4 | N | Problems with interfacing the sensor tech with the devlopment board we will use | Jacob | Technical | High | Avoid | We are using a laptop as our computer and the radar we bought has MATLAB API. The interface has been easy to use. The difficulty is processing the sensor data.
R5 | N | Having problems interfacing the information that the sensors pick up to the user | Joel | Technical | High |  | Make sure that we have our interface all set up, and we are able to somehow get the information that the sensors pick up to the user
R6 | N | The parts we order do not come in | Michaela | Financial/Schedule | Low |  | We will make sure we have the order information up to date, and have a back up store we can go to if something goes wrong.
R7 | N | The initial drive we have starts to wear off and we slow down in development | Miguel | Schedule | Low |  | Keep each member up to date, and make sure that we hold each other accountable for what we are doing. I am making sure that we all get to meetings, and that we are all updated on anything.
R8 | N | Lack of resources at school can cause us to get a little behind | Miguel | Other | Medium |  | This happens to every team. We have all dealt with it, and we will make sure to follow the advice given in 401 and look for other solutions. We made sure to get anything we needed ahead of time. I got a development board from peralta for prototyping purposes.
R9 | N | The Project does not meet the needs of the IP and we solved another issue but not theirs | Joel | Other | low |  | We will make sure that we are in constant contact with the Airforce to make sure we are solving their question
R10 | N | Sensors do not perform as well as expected (quality of data is unnacceptably low) | Jacob | Technical | Medium |  | The radar we bought is easily able to see through walls and detect movig objects.
R11 | Y | Finding Sensor/imaging tech will prove to be difficult, and a lot of research will have to go into it | Miguel | Technical | Medium |  | Having trouble finding possible imaging and senor tech that is able to gather data through walls. Finding this information can prove difficult since none of us have the technical expertise to do so.
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
R41
R42
R43
R44
R45
R46
R47
R48
R49
R50
R51
R52
R53
R54
R55
R56
R57
R58
R59
R60
R61
R62
R63
R64
R65
R66
R67
R68
R69
R70
R71
R72
R73
R74
R75
R76
R77
R78
R79
R80
R81
R82
R83
R84
R85
R86
R87
R88
R89
R90
R91
R92
R93
R94
R95
R96
R97
R98
R99
R100

## Project Contact Information
Project Name | Project | First Name | Last Name | Role | Website | Email | Phone | Mailing Address | Citizenship | Time Zone | Skype | Comments
ASU EGR401/402 | Various | Sangram | Redkar | ASU Professor PM |  | ssredkar@gmail.com | (480) 727-1129 |  | U.S. | MST
| Various | Sangram | Redkar | Industry Partner |  | ssredkar@gmail.com | (480) 727-1129 |  | U.S. | MST |  | Point of Contact for Airforce
| Various | Mubin | Mahmood | EGR 401 Professor |  | Mubin.Mahmood@asu.edu

## Gantt Chart Example
Updated: | 2018-09-17
Milestone or Deliverable (One Week Duration) |  | Resp Initials | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22
Number | Title |  | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due | Due
M1 | Project Plan (Sample entries) |  | 2018-09-24: EXAMPLES
M2 | Course Deliverables |  | 2018-09-24: 2018-09-22; 2018-10-01: Completed (Note: Blue changed to green)
M3 | TSR's |  | 2018-09-24: 2018-09-27; 2018-10-01: 2018-10-03
M4 | ISR's |  | 2018-09-24: 2018-09-26; 2018-10-08: 2018-10-09
M5 | Team Charter |  | 2018-09-24: 2018-09-24; 2018-10-15: 2018-10-17
M6 | Etc
M7 | Problem Definition |  | 2018-10-01: Planned Task
M8 | Problem Statement |  | 2018-10-01: Completed task
M9 | Problem Scope |  | 2018-10-01: Late Task less than 1 week
M10 | Etc |  | 2018-10-01: Late Task more than than 1 week
M11 | Requirements
M12 | Document Key Customers
M13 | Document Customers Interviews
M14 | Document Functional Needs (simple, testable)
M15 | Document customer success criteria
M16 | Etc
M17 | Conceptual Design
M18 | Benchmarking of existing solutions
M19 | Document at least 3 possible concepts
M20 | Document a decision Matrix for the concepts
M21 | Select and initial Concept for go forward
M22 | Etc
M23 | Analysis
M24 | Document go forward design
M25 | Create project plan to create prototype
M26 | Create a High-Level test Plan
M27 | etc
M28 | Prototyping
M29 | Document material list
M30 | Procure materials
M31 | Identify facilities for manufacturing
M32 | Create prototype
M33 | Document a detailed test plan
M34 | Etc
M35 | Testing
M36 | Conduct a test readiness review (Documents,parts,facility)
M37 | Conduct and document test
M38 | Analyze the test results
M39 | Document design changes
M40 | Retest the new design
M41 | ETC
M42 | Final Communication and Documentation
M43 | Planning for the test/Project report
M44 | Planning displays/activities for the showcase
M45 | Create a draft of the project report and get reviews
M46 | Make adjustments - Final Report
M47 | Create materials for the Showcase
M48 | Etc
M49
M50
M51
M52
M53
M54
M55
M56
M57
M58
M59
M60
M61
M62
M63
M64
M65
M66
M67
M68
M69
M70
M71
M72
M73
M74
M75
M76
M77
M78
M79
M80
M81
M82
M83
M84
M85
M86
M87
M88
M89
M90
M91
M92
M93
M94
M95
M96
M97